## Project Tracker
📋 PROJECT PLANNING TRACKER
Website Redesign Project ¦ Team: Digital Squad ¦ Duration: Apr – Jun 2026
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Status | Priority | Milestone? | Depends On (Task ID) | Auto Flag | Notes
▶ Phase: Discovery
T-01 | Kickoff Meeting | Laxmi Sri Sai | 2026-04-01 | 2026-04-01 | 0 | Completed | High | Yes | — | ✅ Done | Align all stakeholders on goals & scope
T-02 | Requirements Gathering | Priya Sharma | 2026-04-02 | 2026-04-07 | 5 | Completed | High | No | T-01 | ✅ Done | Collect feature requests from business units
T-03 | Competitor Analysis | Ravi Kumar | 2026-04-03 | 2026-04-09 | 6 | Completed | Medium | No | T-01 |  | Benchmark 5 competitor websites
▶ Phase: Planning
T-04 | Define Project Scope | Laxmi Sri Sai | 2026-04-10 | 2026-04-11 | 1 | Completed | High | Yes | T-02 | ✅ Done | Document in scope / out of scope items
T-05 | Create WBS | Ananya Reddy | 2026-04-12 | 2026-04-14 | 2 | Completed | High | No | T-04 | ✅ Done | Break project into deliverable components
T-06 | Build Gantt Chart | Laxmi Sri Sai | 2026-04-14 | 2026-04-16 | 2 | Completed | Medium | No | T-05 | ✅ Done | Use Google Sheets timeline view
T-07 | Budget Estimation | Priya Sharma | 2026-04-15 | 2026-04-17 | 2 | Completed | High | No | T-04 | ✅ Done | Estimate cost across 4 budget heads
▶ Phase: Design
T-08 | Wireframes – Homepage | Sneha Rao | 2026-04-20 | 2026-04-25 | 5 | Completed | High | No | T-05 | ✅ Done | Lo-fi wireframes in Figma
T-09 | UI Style Guide | Sneha Rao | 2026-04-24 | 2026-04-30 | 6 | Completed | Medium | No | T-08 | ✅ Done | Colors, fonts, spacing, button styles
T-10 | Design Review & Approval | Laxmi Sri Sai | 2026-05-01 | 2026-05-02 | 1 | Completed | High | Yes | T-09 | ✅ Done | Sign-off from Product & Marketing heads
▶ Phase: Development
T-11 | Frontend Dev – Homepage | Kiran Dev | 2026-05-05 | 2026-05-20 | 15 | Completed | High | No | T-10 | ✅ Done | HTML/CSS/JS implementation
T-12 | Backend Integration | Kiran Dev | 2026-05-15 | 2026-05-28 | 13 | In Progress | High | No | T-11 | ⚠️ Overdue | API connections & CMS setup
T-13 | QA Testing | Ananya Reddy | 2026-05-29 | 2026-06-05 | 7 | Not Started | Medium | No | T-12 | ⚠️ Overdue | Cross-browser & mobile testing
▶ Phase: Launch
T-14 | UAT Sign-off | Laxmi Sri Sai | 2026-06-06 | 2026-06-07 | 1 | Not Started | High | Yes | T-13 | ⚠️ Overdue | Final client sign-off before go-live
T-15 | Website Go-Live | Kiran Dev | 2026-06-10 | 2026-06-10 | 0 | Not Started | High | Yes | T-14 | ⚠️ Overdue | Deploy to production server
Formulas:
Auto Flag = IF([Status]="Completed","✅ Done",IF(AND([End Date]<TODAY(),[Status]<>"Completed"),"⚠️ Overdue",IF([Status]="Blocked","🔴 Blocked","🟢 On Track")))

## Dashboard
📊 PROJECT DASHBOARD — Website Redesign
TASK STATUS SUMMARY |  | MILESTONES
Not Started | 3 | Total Milestones | 5
In Progress | 1
Completed | 11 | OVERDUE TASKS
Blocked | 0 | Overdue (not completed) | 4
At Risk | 0
TOTAL | 15
PRIORITY BREAKDOWN
High | 11
Medium | 4
Low | 0