## Project Tracker
📋 PROJECT PLANNING TRACKER
Website Redesign Project ¦ Team: Digital Squad ¦ Duration: Apr – Jun 2026
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Status | Priority | Milestone? | Depends On (Task ID) | Auto Flag | Notes
▶ Phase: Discovery
T-01 | Kickoff Meeting | Laxmi Sri Sai | 2026-04-01 | 2026-04-01 | 0 | Completed | High | Yes | — | ✅ Done | Align all stakeholders on goals & scope
T-02 | Requirements Gathering | Priya Sharma | 2026-04-02 | 2026-04-07 | 5 | Completed | High | No | T-01 | ✅ Done | Collect feature requests from business units
T-03 | Competitor Analysis | Ravi Kumar | 2026-04-03 | 2026-04-09 | 6 | Completed | Medium | No | T-01 |  | Benchmark 5 competitor websites
▶ Phase: Planning
T-04 | Define Project Scope | Laxmi Sri Sai | 2026-04-10 | 2026-04-11 | 1 | Completed | High | Yes | T-02 | ✅ Done | Document in scope / out of scope items
T-05 | Create WBS | Ananya Reddy | 2026-04-12 | 2026-04-14 | 2 | Completed | High | No | T-04 | ✅ Done | Break project into deliverable components
T-06 | Build Gantt Chart | Laxmi Sri Sai | 2026-04-14 | 2026-04-16 | 2 | Completed | Medium | No | T-05 | ✅ Done | Use Google Sheets timeline view
T-07 | Budget Estimation | Priya Sharma | 2026-04-15 | 2026-04-17 | 2 | Completed | High | No | T-04 | ✅ Done | Estimate cost across 4 budget heads
▶ Phase: Design
T-08 | Wireframes – Homepage | Sneha Rao | 2026-04-20 | 2026-04-25 | 5 | Completed | High | No | T-05 | ✅ Done | Lo-fi wireframes in Figma
T-09 | UI Style Guide | Sneha Rao | 2026-04-24 | 2026-04-30 | 6 | Completed | Medium | No | T-08 | ✅ Done | Colors, fonts, spacing, button styles
T-10 | Design Review & Approval | Laxmi Sri Sai | 2026-05-01 | 2026-05-02 | 1 | Completed | High | Yes | T-09 | ✅ Done | Sign-off from Product & Marketing heads
▶ Phase: Development
T-11 | Frontend Dev – Homepage | Kiran Dev | 2026-05-05 | 2026-05-20 | 15 | Completed | High | No | T-10 | ✅ Done | HTML/CSS/JS implementation
T-12 | Backend Integration | Kiran Dev | 2026-05-15 | 2026-05-28 | 13 | In Progress | High | No | T-11 | ⚠️ Overdue | API connections & CMS setup
T-13 | QA Testing | Ananya Reddy | 2026-05-29 | 2026-06-05 | 7 | Not Started | Medium | No | T-12 | ⚠️ Overdue | Cross-browser & mobile testing
▶ Phase: Launch
T-14 | UAT Sign-off | Laxmi Sri Sai | 2026-06-06 | 2026-06-07 | 1 | Not Started | High | Yes | T-13 | ⚠️ Overdue | Final client sign-off before go-live
T-15 | Website Go-Live | Kiran Dev | 2026-06-10 | 2026-06-10 | 0 | Not Started | High | Yes | T-14 | ⚠️ Overdue | Deploy to production server
Formulas:
Auto Flag = IF([Status]="Completed","✅ Done",IF(AND([End Date]<TODAY(),[Status]<>"Completed"),"⚠️ Overdue",IF([Status]="Blocked","🔴 Blocked","🟢 On Track")))

## Dashboard
📊 PROJECT DASHBOARD — Website Redesign
TASK STATUS SUMMARY |  | MILESTONES
Not Started | 3 | Total Milestones | 5
In Progress | 1
Completed | 11 | OVERDUE TASKS
Blocked | 0 | Overdue (not completed) | 4
At Risk | 0
TOTAL | 15
PRIORITY BREAKDOWN
High | 11
Medium | 4
Low | 0

## 📚 Learning Guide
STEP-BY-STEP LEARNING GUIDE - Project Planning Tracker
Step | What to Do | How to Do It (Exact Steps in Excel)
1 | Open Project Tracker sheet | Click the 'Project Tracker' tab at the bottom. This is your main working sheet with all 15 tasks pre-loaded.
2 | Understand the columns | Task ID = unique code ¦ Owner = who does it ¦ Status = current state ¦ Priority = urgency level ¦ Milestone = key checkpoint ¦ Auto Flag = formula watching deadlines.
3 | Change a task Status | Click any cell in column G (Status). A dropdown arrow appears. Click it, select 'In Progress'. Watch the cell turn YELLOW automatically via conditional formatting!
4 | Mark a task Completed | Click a Status cell, select 'Completed'. Cell turns GREEN. Now look at column K (Auto Flag) -- it shows Done automatically because of the IF formula.
5 | See the Auto Flag formula | Click cell K4. Look at the formula bar at the top. You will see an IF formula that checks Status and End Date to flag overdue tasks. This is the core PM logic.
6 | Understand how overdue works | Change Task T-01 End Date (column E) to yesterday. Check column K -- it shows Overdue! Change Status to Completed -- flag clears. This is milestone tracking in action.
7 | Add your own task | Scroll to the bottom of any phase. Click an empty row. Type Task ID T-16, fill in name/owner/dates. Copy the Auto Flag formula from K4 and paste into your new row column K.
8 | Filter by Priority | Click any header cell, go to Data tab, click AutoFilter. Click the Priority dropdown in column H, uncheck all, check High only. Now only High priority tasks show. Clear filter when done.
9 | Open the Dashboard | Click the 'Dashboard' tab. You will see live counts of tasks by Status and Priority. These update AUTOMATICALLY when you change statuses in the tracker!
10 | Understand COUNTIF formula | On Dashboard, click cell B3. The formula COUNTIF counts all cells in column G of Project Tracker that say 'Not Started'. Change a status and come back -- the number updates live!
11 | Filter by Owner | In Project Tracker, use AutoFilter on the Owner column (C). Filter by your own name to see only your tasks. This simulates how a real PM tracks team workload.
12 | Practice dependency logic | Look at column J (Depends On). T-02 depends on T-01. In a real project T-02 cannot start until T-01 is done. Try marking T-01 as Blocked, then update T-02 status to Blocked too.
13 | Identify Milestones | Filter column I (Milestone?) = Yes. You will see 5 key milestones highlighted in purple: Kickoff, Scope Defined, Design Approved, UAT, and Go-Live.
14 | Save your practice version | File, Save As, rename to MyProjectTracker_Practice.xlsx. Now you have your own copy to experiment with freely without losing the original.
15 | Customise for your own project | Replace task names with tasks from your own project idea (event, study plan, etc). Update owners with your team. Change dates. All formulas and formatting work automatically!